## Absence
Test Case Identifier | Test Case Name | Description | Sl# | Navigation and Steps | Expected Results | Actual Results | Status | Comments
GB-22D-ABSENCE MANAGEMENT-01 | AUTOCOMPLETE RULES FOR CHILDBIRTH AND PLACEMENT DATES BUSINESS OBJECT IN ABSENCE MANAGEMENT | The Childbirth and Placement Dates business object contains planned start date, planned end date and will return to work information based on the ANC_PER_ABS_MATERNITY table. We can now use the new delivered autocomplete rule, Default Planned End Date Based on Planned Start Date, to default the planned end date of a maternity, paternity, or adoption leave based on the planned start date of the absence. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Groups > Person Management > Select Employee > Actions > Record Absence | Should be able to navigate
|  |  | 3 | Enter a leave using the childbirth or placement pattern | Plan to be end dateted 364 days after the start date
GB-22D-ABSENCE MANAGEMENT-02 | CARRYOVER BALANCE CONSUMPTION AND MULTIPLE YEAR CARRYOVER FOR ACCRUAL PLANS | You can now use the carried over balance of accrual plans with no forfeiture limit beyond the 365 day/1 year expiration limit. This applies to both front loaded and incremental accrual plans. Previously, employees had to use their carryover balance within a certain time period before it expired. This period couldn’t be greater than 1 year. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Groups > Person Management > Select Employee > Actions > Record Absence | Should be able to navigate
|  |  | 3 | Go to Plan Balance Page | Should be able to see the remaining balance and the expiration details for each of the carryover sub balances
GB-22D-ABSENCE MANAGEMENT-03 | INCREASED CHARACTER LIMIT FOR SHORT CODE IN CALENDAR EVENTS | The character limit for Short Code in Calendar Events has been raised from 8 to 48. Now when you create calendar events, you get more flexibility regarding short codes. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > Setup and Maintenance > Search Tasks > Manage Calendar Events | Should be able to navigate
|  |  | 3 | Create Calendar Events | Should be able to enter a short code of up to 48 characters
GB-22D-ABSENCE MANAGEMENT-04 | AUDIT ENABLED FOR ACCRUAL TABLES | Audit capability has been added to three absence plan transaction tables. You can use audit to track all the changes that happen in the absence plan tables. Audit even keeps track of the rows that might get deleted. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > Navigator > Tools > Audit Reports | Should be able to navigate
|  |  | 3 | Submit Audit Reports | Should be able to get detailed information about plan enrollments and accrual calculations by auditing absence tables.

## OTL
Test Case Identifier | Test Case Name | Description | Sl# | Navigation and Steps | Expected Results | Actual Results | Status | Comments
GB-22D-TIME AND LABOR MANAGEMENT-01 | STANDARDIZATION OF BUTTON LOGIC IN RESPONSIVE TIME CARDS | Time card Actions buttons now show all actions the person can do, both available or unavailable based on their time entry profile, their security setup, and the time card status. Here's a list of all available and unavailable Actions menu options for workers, line managers, and time and labor managers. The worker time entry profiles, security grants, and time card status determine whether the actions are available or unavailable. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > Time Management > Time Cards | Should be able to navigate
|  |  | 3 | Select transaction & Action | Time card Actions buttons should show all actions the person can do
GB-22D-TIME AND LABOR MANAGEMENT-02 | INTEGRATION WITH THE DELETE ASSIGNMENT PROCESS IN GLOBAL HUMAN RESOURCES | Oracle Fusion Global Human Resources prevents a delete assignment process from completing with success if the assignment has time cards. More precisely, the process calls a time and labor API that identifies any existing time card for an assignment that the process should delete. This call happens when the process was started from an HR page. To move forward, a time and labor manager needs to manually delete the time cards, or time entries reported against the assignment. When they finish, run the delete assignment process again. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Groups > Person Management > Select Employee | Should be able to navigate
|  |  | 3 | Delete Assignment that has time cards | Should be able to see the error message
GB-22D-TIME AND LABOR MANAGEMENT-03 | ENHANCED ORACLE TIME AND PAYROLL RECONCILIATION EXTRACT | We enhanced the Time and Payroll Info for Reconciliation extract with the new Include reconciled rows? parameter. Use this parameter to exclude or include information with no differences between Time and Labor and Global Payroll in the extract. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Groups > Data Exchange > Submit Extract | Should be able to view Time Card foremployees accoring to the selected filter
|  |  | 3 | Submit Time and Payroll Info for Reconciliation extract with the new Include reconciled rows? Parameter | Output should be generated based on the parameter used
GB-22D-TIME AND LABOR MANAGEMENT-04 | TEAM SCHEDULE SELF-SERVICE PAGES ENHANCEMENTS | When you enable multiple assignments, line managers and time and labor managers can filter their team schedules by offer and pending worker assignments. By default, they see contingent workers and employees. Individuals can't see the schedules for their peers' offer and pending assignments. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > Time Management > Team Schedule | Should be able to navigate
|  |  | 3 | Check Worker Type filter | Should be able to filter team schedules by offer and pending worker assignments.
GB-22D-TIME AND LABOR MANAGEMENT-05 | GENERATE TIME CARDS ENHANCEMENT | Time and Labor managers can now directly access the Generate Time Cards task from the Tasks panel tab of the Time Management area or using the new quick action. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > Time Management > Time Management Overview | Should be able to navigate
|  |  | 3 | Click on Task | Should be able to see Generate Time Cards on the Tasks panel tab

## Global Payroll
Test Case Identifier | Test Case Name | Description | Sl# | Navigation and Steps | Expected Results | Actual Results | Status | Comments
GB-22D-GLOBAL PAYROLL-01 | AUTOCOMPLETE RULES FOR FINAL CLOSE DATE (PAYROLL ASSIGNMENT OBJECT) IN THE TERMINATION FLOW Feature is from a customer submitted idea. | We can derive the Final Close date in 2 different ways. As a predefined (static) date or a derived date (dynamic). Autocomplete rules will be supported in the "Terminate" transaction. This action type is valid for both defaulting options (static and dynamic). | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Person Management > Select Employee | Should be able to navigate
|  |  | 3 | Perform transaction according to the rule set up | Outcome should be according to the autocomplete rule set up
GB-22D-GLOBAL PAYROLL-02 | AUTOCOMPLETE RULES FOR TAX REFERENCE UNIT (IN THE PAYROLL TERMS BUSINESS OBJECT) IN HR FLOWS | When you create rules, you must select the Rule Type as "Field Modification Rule Type". The Business Object is "Payroll Terms", and the Field value is "Default Payroll Values Indicator". | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Workforce Management | Should be able to navigate
|  |  | 3 | Perform transaction according to the rule set up | Outcome should be according to the autocomplete rule set up
GB-22D-GLOBAL PAYROLL-03 | NEW PAYROLL DUTY ROLES | New duty roles, one each to secure different subject areas of payroll are created. With this, customers can provide access to individual subject areas within payroll module. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > Tools > Reports and Analytics | Should be able to navigate
|  |  | 3 | Create a new analysis | Subject areas should be visible according to duty role attached
GB-22D-GLOBAL PAYROLL-04 | PAYROLL TASKS IN PERSON SPOTLIGHT | Professional payroll users can see their workers' information in the Person Spotlight Page, and take certain actions depending on the security configuration of their role. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group | Should be able to navigate
|  |  | 3 | Select Person Spotlight | See workers' information
GB-22D-GLOBAL PAYROLL-05 | COPY FUTURE DATED CHANGES DURING GLOBAL TRANSFER | You can now copy the future-dated changes and preserve end dates on calculation cards and person costing overrides during a Global Transfer. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Person Management > Select Employee | Should be able to navigate
|  |  | 3 | Perform Global Transfer | Future-dated changes and end dates on calculation cards and person costing should be copied
GB-22D-GLOBAL PAYROLL-06 | ADD NEW INPUT VALUES TO UNUSED ELEMENTS | You can now add a new input value to an element as long as the entry does not exist or the element is not processed. Previously, if a payroll process was executed after creation of an element, adding a new input value was not allowed even if the element was not used. With this enhancement, you can add the input values till the element has either an element entry or a run result. The run result scenario is for the indirect elements which do not have entries. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Compensation > Elements | Should be able to navigate
|  |  | 3 | Add input values to unused element | Should be able to add new input value to the element
GB-22D-GLOBAL PAYROLL-07 | AUTOMATICALLY ADD BALANCE RUN DIMENSIONS | When you use the Balance Definition page and add or update a group level balance, the associated run dimensions are added automatically. The application checks for all related 'Run' balances and adds them if not included. If the run dimensions aren’t added, downstream issues occur in the payroll run and reporting. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Balance Definition | Should be able to navigate
|  |  | 3 | Add new balance dimension | Run dimensions should get automatically added
GB-22D-GLOBAL PAYROLL-08 | CALCULATION ENTRIES DISPLAY RESERVED INPUT VALUES | You can view the following additional reserved input values in the Standard Entries section of the Calculation Entries page. This enhancement provides a better user experience while displaying the calculation entries. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Groups > Payroll > Person Results > Enter employee name in Search for Person field. | Should be able to navigate
|  |  | 3 | Navigate to Calculation Entries page | Should be able to view additional reserved input values in the Standard Entries section
GB-22D-GLOBAL PAYROLL-09 | EVENT SUPPORT FOR HCM RATES | With this enhancement, use the new event actions solution to control which employees should have rates calculated. This feature limits the number of employees that have rates recalculated and thereby improves the performance of the rates calculation process. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Run the Process Event Action flow | Should recalculate rates for all employees with a rates event notification
GB-22D-GLOBAL PAYROLL-10 | SUPPORT FOR TIME UPDATES IN PAYROLL: UPGRADE TIME ELEMENTS | You can now load time card updates to payroll for all time elements created prior to Update 22C. Time card information from Time and Labor or a third-party time product can be loaded into the payroll application for payment. When you make any changes to the time card only the updated time information is sent to payroll. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Submit Run Feature Upgrade flow | Should load time card updates to payroll for all time elements
GB-22D-GLOBAL PAYROLL-11 | OPTIMIZE PERFORMANCE OF MULTI-THREADED PROCESSES | The new multi-thread feature automatically identifies and assigns the number of threads and the chunk size to optimize the process. This automatic multi-thread feature supports all multi-threaded payroll processes such as Calculate Payroll and Make EFT Payments. It also supports predefined HCM Extracts such as the Gross-to-Net report and user-defined extracts. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Submit Gross-to-Net report with Maximum Number of Threads action parameter | Performance of the payroll processes should be optimized
GB-22D-GLOBAL PAYROLL-12 | VIEW RUN RESULTS WITH ELEMENT ENTRY RESULT IDENTIFIER | You can now use the new Element Entry Result Identifier attribute to easily identify the results for each entry. This attribute is especially useful when you have multiple entries of the same element in your run results export file. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Groups > Payroll > Person Results > Enter employee name in Search for Person field. | Should be able to navigate
|  |  | 3 | Choose Run Results from the Actions | Should be able to view Element Entry Result Identifier attribute
GB-22D-GLOBAL PAYROLL-13 | NEW PROCESS EVENT ACTION FLOW FOR MANUAL EVENT ACTIONS | You can now use event groups and event actions to control which employees are included in the processes, such as to generate HCM Rates and time card reprocessing. When you define an event action, you specify whether the submission of the action is automatic or manual. If the event action is a manual submission type, you can use the ‘Process Event Action’ flow to submit the process associated to the event action. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Run Process Event Action flow | Should calculate rates for all employees with an unprocessed rate event notification
GB-22D-GLOBAL PAYROLL-14 | FLOW MESSAGES IN CSV FORMAT | When you submit the Calculate Payroll flow, the flow automatically generates the errors and warning messages CSV file. After you submit the flow, navigate to the Process Results Details page from the Checklist or Summary Results page and access the CSV file from the Output and Log Files section. You can view the error and warning messages and take corrective action for the flow. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Submit Calculate Payroll with Auto Generate Errors and Warnings File action parameter | Flow should automatically generate the errors and warning messages CSV file.
GB-22D-GLOBAL PAYROLL-15 | CANCEL ACTION | Use the Cancel action in the Checklist and Results Summary UIs to cancel all ESS threads of a flow task that are in In Progress status. A process can get stuck and have In Progress status due to various reasons. It could be due to process time lapse, an infrastructure issue such as a network failure, or an ESS failure due to patching, and so on. You would want to cancel the jobs that are stuck, take corrective action, and resubmit the process. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Use the Cancel action in the Checklist and Results Summary | Should cancel all ESS threads of a flow task that are in In Progress status
GB-22D-GLOBAL PAYROLL-16 | LOGGING AND MONITORING FOR THE PAYROLL BACKGROUND PROCESS | Use the Payroll Background Logging and Monitoring flow to identify and resolve payroll queries for features that use the payroll background process. This flow is useful for those who manage customer environments, test payroll processes, and troubleshoot issues with payroll processes. For example, your system administer can use this flow to generate log files for features that uses the payroll background flow such as Anytime Pay. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Submit Payroll Background Logging and Monitoring flow | Should generate log files for features that uses the payroll background flow such as Anytime Pay
GB-22D-GLOBAL PAYROLL-17 | VIEW PAYROLL COSTING RESULTS FOR A SUBLEDGER JOURNAL ENTRY | You can now review the payroll costing results for a subledger journal entry from the Subledger Journal Lines page with the general ledger role. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to General Accounting > Journals > Review Subledger Journals | Should be able to navigate
|  |  | 3 | View Journal Entry > View Transaction | Should be able to review the payroll costing results
GB-22D-GLOBAL PAYROLL-18 | INTERMEDIARY BANK ACCOUNT DETAILS IN PAYMENTS XML | You can now include intermediary bank account details, now stored in the Payments XML, in the EFT file when it's required to facilitate an inter-country payment. For example, intermediary bank accounts are used to route payments when an employer's US based bank doesn't have relationships with banks in the developing world. The payments are sent from your company bank account to the intermediary bank account, and onto the employee’s bank account. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Submit Make EFT Payment | Should include intermediary bank account details in the EFT file
GB-22D-GLOBAL PAYROLL-19 | PREVIEW PAYSLIPS AND YEAR-END DOCUMENTS | You can now easily preview payslips and year-end PDF documents directly from the Payslip and Year-End Documents pages without having to download. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > Me > Year-End Documents | Should be able to navigate
|  |  | 3 | View Payslips | Should be able easily preview payslips PDF documents without having to download
GB-22D-GLOBAL PAYROLL-20 | PAYROLL CORE SUPPORT FOR DEFAULTING TAX REPORTING UNIT | Users who have defined an international payroll legislation such as United Nations, can now automatically assign a Tax Reporting Unit (TRU) to newly hired employees. The TRU will trigger the creation of a deduction card for the employee and the necessary TRU and assignment associations. This information ensures the international employee can be successfully processed in the Calculate Payroll process. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group | Should be able to navigate
|  |  | 3 | Hire an Employee | TRU defined for the organization should be assigned to the employees

## UK Payroll
Test Case Identifier | Test Case Name | Description | Sl# | Navigation and Steps | Expected Results | Actual Results | Status | Comments
GB-22D-UK PAYROLL-01 | GLOBAL TRANSFER FOR STUDENT LOAN AND POSTGRADUATE LOAN COMPONENTS WITH FUTURE-DATED UPDATES | You can now copy future-dated updates for the Court Order and Student Loans calculation cards during the global transfer process. The application creates Student Loan or Postgraduate Loan components only if the calculation card in the source legal employer contains these components. The student loan or postgraduate loan components are effective as of the global transfer date or after the global transfer date. But the start date of the new calculation card that's created is as of the transfer date. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Group > Person Management > Select Employee | Should be able to navigate
|  |  | 3 | Perform Global transfer | Future-dated updates for the Court Order and Student Loans on calculation cards should be copied

## US Payroll
Test Case Identifier | Test Case Name | Description | Sl# | Navigation and Steps | Expected Results | Actual Results | Status | Comments
GB-22D-US PAYROLL-01 | START-OF-YEAR FLOW ENHANCEMENT FOR EXEMPT DETAILS UPDATE OPTIONS | We have enhanced the Start-of-Year flow with the inclusion of additional options when running the Exempt details update data type. These new options allow more flexibility when resetting exemptions on the tax card. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Submit Start-of-Year flow | Should be able to see additional options when running the Exempt details update
GB-22D-US PAYROLL-02 | START-OF-YEAR FLOW ENHANCEMENT FOR 457 LIMIT UPDATE | We have enhanced the Start-of-Year flow when running the 457 limit update data type. The flow now end-dates the Accumulated Under-Utilized Contributions for Special 457 (b) Catch-Up calculation value on the Benefits and Pensions card as of 12/31 for the previous effective year. This feature will help users ensure they enter the updated under-utilized contribution amount for each eligible employee for the upcoming year. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Submit Start-of-Year flow | Should end-dates the Accumulated Under-Utilized Contributions for Special 457 (b) Catch-Up calculation value on the Benefits and Pensions card as of 12/31 for the previous effective year
GB-22D-US PAYROLL-03 | PERFORM MULTIPLE TAX BALANCE ADJUSTMENTS FOR THIRD-PARTY PAYMENTS USING HCM DATA LOADER | We have made it easier for you to perform tax balance adjustments for third-party payments for multiple employees. You can now use HCM data loader (HDL) to perform these balance adjustments in one batch for common payroll transactions, such as third-party sick pay, stock option exercises, and moving and relocation transactions. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > My Client Groups > Data Exchange > Import and Load Data | Should be able to navigate
|  |  | 3 | Upload the HDL file & run Adjust Multiple Balances flow | Should be able to see balance adjustment
GB-22D-US PAYROLL-04 | PERIODIC PAYROLL ARCHIVE ENHANCEMENT TO CAPTURE EMPLOYER PHONE NUMBER | We have augmented the Periodic Payroll Archive process to capture your employer phone number defined at the legal reporting unit level. This enables you to include it on your employee payslips. This feature satisfies the legislative requirements for New York, Hawaii, and Oregon. | 1 | Login to the application | Login should be successful
|  |  | 2 | Navigate to Home > Payroll > Submit a Flow | Should be able to navigate
|  |  | 3 | Submit Periodic Payroll Archive & Generate Payslip process | Should be able to see employee phone number on employee payslip.